## Sheet1
RNLI Tester | Version | DATE | ZONE | ISSUE | Rectified Y/N? | Rectified by | Date
Paul Savage | PC - safari on Mac | 26.3.12 | Disclaimer | Change look of logo buttons on disclaimer page - suggest same colour background at the top navy blue bar. Then use the same android logo, but a simple white apple logo and the PC logo can be the same - but wording "PC/MAC" | y | Tez | 2012-03-27
Paul Savage | PC - safari on Mac | 26.3.12 | throughout | On the top menu bar logo with the star of life logo, suggest using the Lifeboats with white letters logo as you can't see the blue letters. | Y | Tez | 2012-03-27
Paul Savage | PC - safari on Mac | 26.3.12 | Triage | I think I would like to see the spreadsheet for all the triage data as I'm uneasy about some of the info that you have been sent. Sorry. | Y | Tez | 2012-03-27
Paul Savage | PC - safari on Mac | 26.3.12 | Pat Ass | Unconscious ill, unconscious injured and manual airway manoeuvres ( patient assessment zone) - once initial button is pressed - top menu bar says "conscious injured" on both the menus ( video and check card) | Y | Tez | 2012-03-27
Paul Savage | PC - safari on Mac | 26.3.12 | Kit zone | Entonox kit, first page ( front of checkcard) says "BACK and HOME" not BACK and NEXT | y | Tez | 2012-03-27
Paul Savage | PC - safari on Mac | 26.3.12 | Kit zone | Kit zone. ILB new red bag and old bag. ITEM BR-0070 x4 should also link to eyewash | N | Sean | 2012-03-28
Paul Savage | PC - safari on Mac | 26.3.12 | Kit zone | Oxygen kit card. When the Bag Valve mask is selected, top menu says 'PUMP" it needs to say "BAG VALVE MASK" | Y | Tez | 2012-03-27
Paul Savage | PC - safari on Mac | 26.3.12 | Kit zone | Entonox kit, on the page with the kit shown, "HOME" doesn't work every time?? | Y | Tez | 2012-03-27
Paul Savage | mobile - iphone 4s | 26.3.12 | throughout | On the top menu bar logo with the star of life logo, suggest using the Lifeboats with white letters logo as you can't see the blue letters. | Y | Tez | 2012-03-27
Paul Savage | mobile - iphone 4s | 27.3.12 | home page | No disclaimer page on start of app. | Y |  | 2012-03-27
Paul Savage | mobile - iphone 4s | 27.3.12 | MCQ | On MCQ, when Injury button selected, top blue menu bar displays "all Questions" not "Injury Questions" | Y | Tez | 2012-03-27
Paul Savage | mobile - iphone 4s | 27.3.12 | MCQ | On MCQ, when Immersion button selected, top blue menu bar displays "all Questions" not "Immersion Questions" | Y | Tez | 2012-03-27
Paul Savage | mobile - iphone 4s | 27.3.12 | MCQ | On MCQ, when Ilness button selected, top blue menu bar displays "core Questions" not "llness Questions" | Y | Tez | 2012-03-27
Paul Savage | mobile - iphone 4s | 27.3.12 | Kit zone | on LG casualty care response bag the blue top menu bar states "Lifeguard First Aid and combined" it needs to say "Lifeguard Casualty Response bag" | Y | Tez | 2012-03-27
Paul Savage | mobile - iphone 4s | 27.3.12 | throughout | several images aren't loading and are replaced with ? Especially in the kit zone and its word docs | Y | Tez | 2012-03-27